## Start here
Online store launch checklist
A free template by JIN Design. Example rows are for a fictional Singapore business (Harbour Bake Supplies Pte Ltd), shown as at 9 November 2026, a week before launch. Replace them with your own.
How to use it
1. Fill in your store details below, including your launch date. Every due date in the checklist is worked out from it, so a new launch date moves the whole plan.
2. Work through the tabs in order. Rows marked with a platform other than "All" only apply to that platform; the Platform note says what changes on Shopify, WooCommerce or a custom build.
3. Give every task an owner and set the status from the dropdown. Change "Days from launch" if a task needs more or less time.
4. Log every test order on the Test orders tab, including PayNow, a refund and a trade or discount order. Retest anything marked Fail.
5. After launch, keep the First 30 days tab open and compare orders in your store admin with GA4 every week.
Your store
Business | Harbour Bake Supplies Pte Ltd (fictional example)
Store address | www.harbour-bake.example
Platform | WooCommerce
Launch date | 2026-11-16
Payment gateway | Gateway with a WooCommerce plugin that lists PayNow and cards
GST-registered? | Yes
Customers | Cafés and bakeries on trade prices, home bakers on retail prices
Who builds and maintains it | Agency, with the ops lead running daily order checks
Where logins are kept | Company password manager. Never store passwords in this file.
Progress
Checklist | Tasks | Done | In progress | Blocked | Not applicable | Not started | % complete
Setup | 18 | 14 | 2 | 1 | 1 | 0 | 82.35%
Catalogue and content | 13 | 7 | 3 | 0 | 0 | 3 | 53.85%
Checkout and testing | 14 | 10 | 3 | 0 | 0 | 1 | 71.43%
Tracking | 10 | 6 | 2 | 0 | 0 | 2 | 60%
Launch day | 10 | 0 | 0 | 0 | 0 | 10 | 0%
First 30 days | 12 | 0 | 0 | 0 | 0 | 12 | 0%
Test orders: passed / failed | 4 | 2
Status meanings
Not started | Not done yet.
In progress | Someone is working on it.
Done | Finished and checked.
Blocked | Waiting on someone or something. Say what in Notes.
Not applicable | Does not apply to your store or platform.
Good to know (checked 15 October 2026)
GST-registered stores must show prices that include GST, including on websites. Breaking the price display rules can lead to a fine of up to S$5,000.
IRAS: displaying and quoting prices
Businesses may not add a surcharge for PayNow payments.
ABS: PayNow
Marketing consent cannot be a condition of buying. SMS and call marketing to Singapore numbers needs a Do Not Call Registry check (results valid 21 days) unless you hold clear consent.
PDPC: Advisory Guidelines on the Do Not Call Provisions
Enterprise Singapore's PSG ceased on 29 September 2026; new applications have gone under the EDGE Grant since 30 September. A pre-approved E-Commerce Online Shop (B2C) package can get up to 50% support for SMEs, on software costs capped at S$5,000. Apply before any work or deposit.
Enterprise Singapore: E-Commerce Online Shop (B2C)
These are summaries, not legal or tax advice. Check the current rules on each official page before relying on them.
About this template
Made by JIN Design, a web design and development studio in Singapore. Free to use for your own website and for websites you manage for clients. Please do not resell the file.
Template page and instructions: jin-design.com/resources/templates/online-store-launch-checklist/
Guide: how to plan an online store in Singapore, with platforms, PayNow and GST
Ecommerce website design and development by JIN Design

## Setup
Setup: legal, payments, delivery and tax
Legal, payments, delivery and tax. Start four to six weeks before launch. Example rows are for Harbour Bake Supplies Pte Ltd, a fictional baking supplies wholesaler on WooCommerce.
# | Area | Task | Done when | Platform | Platform note | Owner | Days from launch | Due date | Status | Notes
1 | Legal | Publish terms of sale and a returns and refunds policy | The policy says how long customers have to return items, who pays for return delivery, how refunds are paid and what happens with faulty goods. It is linked from the footer, every product page and the checkout. | All |  | Director | -21 | 2026-10-26 | Done | Lemon law: a defect found within 6 months of delivery is presumed to have existed at delivery.
2 | Legal | Update the privacy policy for the store | It lists what checkout collects, why, who receives it (payment gateway, courier, email platform, accounting software) and how to contact your data protection officer. | All |  | Director | -21 | 2026-10-26 | Done
3 | Legal | Add a separate marketing consent checkbox | The box is not ticked in advance, names the channels (email, SMS) and is not needed to buy. Consent is saved with the customer record. | All | Shopify: marketing consent options in checkout settings. WooCommerce: email platform plugin or a custom checkout field. Custom: build and store it with the order. | Agency | -14 | 2026-11-02 | Done
4 | Legal | Plan DNC checks before any SMS or call marketing | Numbers are checked against the Do Not Call Registry before sending, and results are no more than 21 days old, unless you hold clear and unambiguous consent. | All |  | Marketing | -7 | 2026-11-09 | In progress | A one-off purchase is not an ongoing relationship under the DNC rules.
5 | Payments | Choose a gateway that offers PayNow on your platform | The gateway's own plugin or app lists PayNow for your platform. Payout timing, refund rules and fees are read on its own pricing page. The provider appears in the MAS Financial Institutions Directory. | All | Shopify: PayNow is not a Shopify Payments method for Singapore, so it comes from a third-party provider; Shopify's third-party transaction fees apply. WooCommerce: the gateway's own plugin. Custom: the gateway's API. | Director | -28 | 2026-10-19 | Done
6 | Payments | Switch on payment methods in test mode | PayNow, cards and any wallets appear at checkout in test or sandbox mode. No surcharge is added for PayNow. | All |  | Agency | -21 | 2026-10-26 | Done | ABS: merchants may not surcharge consumers for PayNow.
7 | Payments | Confirm payouts go to the company bank account | The gateway account and payout account are in the company's name, and the accounts team knows when each payment method pays out. | All |  | Accounts | -21 | 2026-10-26 | Done
8 | Payments | Set up invoices on credit terms for trade customers | Approved trade accounts can choose "Pay by invoice" at checkout, and the invoice shows the agreed terms. | All | Shopify: payment terms are part of B2B, available on the Basic, Grow, Advanced and Plus plans. WooCommerce: B2B extension or custom code. Custom: build to your terms. | Agency | -14 | 2026-11-02 | Done
9 | Shipping | Set delivery zones, methods and charges | Each option has a charge, a service area and an estimated delivery time, and shoppers can see the charge before checkout. | All |  | Ops lead | -21 | 2026-10-26 | Done | Courier, self-collection and next-day for trade orders.
10 | Shipping | Set up self-collection | The collection address, opening hours and "ready for collection" email are set. | All |  | Ops lead | -14 | 2026-11-02 | Done
11 | Shipping | Connect the courier account and print a test label | A test label prints, the pickup schedule is agreed and tracking emails are switched on. | All |  | Ops lead | -14 | 2026-11-02 | Done
12 | Shipping | Write cut-off times and the public holiday notice | Product pages and the delivery page show the daily cut-off for dispatch and any holiday changes. | All |  | Ops lead | -10 | 2026-11-06 | Done
13 | Tax | Confirm your GST status | If GST-registered, all prices shown to the public include GST. If not registered, the store charges no GST, and someone watches turnover against the S$1 million registration test. | All |  | Accounts | -28 | 2026-10-19 | Done | GST-registered.
14 | Tax | Match the store's tax settings to your GST status | Prices are entered with GST included, the cart, checkout, emails and invoices show the same total, and exported orders are zero-rated with the export documents kept. | All | Shopify: Taxes and duties settings. WooCommerce: tax settings, "Prices entered with tax". Custom: tax rules in the code and invoices. | Agency | -14 | 2026-11-02 | Done
15 | Accounts | Connect orders to the accounting software | A test order appears in the accounting software with the right GST, payment method and customer. | All |  | Accounts | -10 | 2026-11-06 | Blocked | Waiting for API access from the accounting software provider.
16 | Upkeep | Agree who updates WordPress, WooCommerce and plugins | A named person or care plan updates WordPress, WooCommerce, plugins, theme and PHP every week, testing on a staging copy first. | WooCommerce | Shopify: Shopify updates the platform; review app and theme updates instead. Custom: agree who updates packages and the server. | Agency | -7 | 2026-11-09 | In progress | Care plan starts on launch day.
17 | Accounts | Put every login in the company's name | Domain, hosting or platform, payment gateway, courier, GA4, Tag Manager and Search Console are owned by the company. Each person has their own login with two-factor sign-in. | All |  | Director | -14 | 2026-11-02 | Done | Never store passwords in this file.
18 | Grant | Check the EDGE Grant before signing anything | If you want support, the E-Commerce Online Shop (B2C) package comes from a pre-approved vendor on SMEs Go Digital, and you apply before any work starts or any deposit is paid. | All |  | Director | -42 | 2026-10-05 | Not applicable | Custom-designed store: our own spend.
Formulas:
Due date = IF(AND(ISNUMBER([Days from launch]),ISNUMBER('Start here'!$B15)),'Start here'!$B15+[Days from launch],"")

## Catalogue and content
Catalogue and content
Products, prices, photos, pages and SEO. Due dates are worked out from the launch date on the Start here tab.
# | Area | Task | Done when | Platform | Platform note | Owner | Days from launch | Due date | Status | Notes
1 | Product data | Complete the product data sheet | Every product has a name, SKU, price with GST, variants, weight and size for delivery, stock level and category. | All | Shopify and WooCommerce: import by CSV. Custom: import into the product database. | Ops lead | -21 | 2026-10-26 | Done | 912 products, 3 price lists.
2 | Product data | Set up trade price lists | A logged-in trade customer sees their own prices. A retail shopper sees retail prices. | All | Shopify: B2B catalogs, available on the Basic, Grow, Advanced and Plus plans, with up to 3 active catalogs below Plus. WooCommerce: B2B pricing extension. Custom: price rules. | Agency | -14 | 2026-11-02 | Done
3 | Photos | Add photos for every product and variant | Photos show scale, texture and each variant, are compressed for the web and have alt text. | All |  | Marketing | -14 | 2026-11-02 | In progress | About 60 products still need photos.
4 | Copy | Write product descriptions that answer buying questions | Each product lists size or weight, ingredients or materials, allergens where relevant, storage and what is in the pack. | All |  | Marketing | -14 | 2026-11-02 | Done
5 | Navigation | Test categories, filters and search | Shoppers can filter by category and type, and search finds products by name, SKU and common misspellings. | All |  | Agency | -10 | 2026-11-06 | Done
6 | Pages | Publish the delivery, returns, FAQ and contact pages | Each page is linked from the footer, and the FAQ answers the questions customers already ask by phone or email. | All |  | Ops lead | -10 | 2026-11-06 | Done
7 | Pricing | Check price displays and promotions | Prices include GST if you are registered, unavoidable charges are in the headline price, optional add-ons are not pre-ticked and no promotion says "no GST". | All |  | Marketing | -7 | 2026-11-09 | In progress
8 | Reviews | Set up review requests after delivery | Reviews come only from real customers after delivery. None are bought or written by staff. | All |  | Marketing | -7 | 2026-11-09 | Not started
9 | Emails | Brand and proofread every order email | Order confirmation, shipped, ready for collection, refunded and invoice emails show the right totals, GST details and how to contact you. | All |  | Agency | -10 | 2026-11-06 | Done
10 | SEO | Write titles, descriptions and clean URLs | Every product and category has a unique title and description, and URLs are short and readable. | All |  | Agency | -7 | 2026-11-09 | In progress
11 | SEO | Map old store URLs to new ones | Every old product and category address has a new home, ready to redirect on launch day. | All |  | Agency | -7 | 2026-11-09 | Done | Test the list with jin-design.com/resources/tools/redirect-checker/
12 | SEO | Add Product structured data | Product pages carry Product markup with name, image, price in SGD and availability, and pass Google's Rich Results Test. | All | Shopify: many themes output it already. WooCommerce: SEO plugin or theme. Custom: add JSON-LD to the product template. | Agency | -7 | 2026-11-09 | Not started | Free schema generator: jin-design.com/resources/tools/schema-generator/
13 | Accessibility | Check contrast, alt text and form labels | Text passes contrast checks, images have alt text and every checkout field has a visible label. | All |  | Agency | -7 | 2026-11-09 | Not started
Formulas:
Due date = IF(AND(ISNUMBER([Days from launch]),ISNUMBER('Start here'!$B15)),'Start here'!$B15+[Days from launch],"")

## Checkout and testing
Checkout and testing
Test every way a customer can pay, receive and return an order. Log each test on the Test orders tab.
# | Area | Task | Done when | Platform | Platform note | Owner | Days from launch | Due date | Status | Notes
1 | Payments | Place a test card order | The order is marked paid, stock goes down and the confirmation email arrives. | All |  | Agency | -10 | 2026-11-06 | Done | Log every test on the Test orders tab.
2 | Payments | Place a test PayNow order | A QR code appears, the order is marked paid by itself after payment, and you know which name customers see in their banking app. | All | Shopify: through the provider's app. WooCommerce: through the gateway plugin. Custom: through the gateway API. | Agency | -10 | 2026-11-06 | Done | Failed the first time in GA4: see Test orders 2 and 6.
3 | Payments | Let a PayNow QR code expire | The order is not marked paid, the customer can start a new payment, and stock is released if the order is abandoned. | All |  | Agency | -10 | 2026-11-06 | Done | On Stripe, PayNow QR codes are valid for 1 hour.
4 | Payments | Place a trade order on invoice terms | A trade customer sees their price list, chooses invoice terms and receives the invoice. | All |  | Ops lead | -8 | 2026-11-08 | Done
5 | Delivery | Test every delivery option and zone | Charges and delivery times are right, and the address form has separate fields for block or house number, street, unit number and 6-digit postal code. | All |  | Ops lead | -10 | 2026-11-06 | Done
6 | Discounts | Test discount codes and the free delivery threshold | Each code applies only where it should, and the total is right just below and just above the threshold. | All |  | Marketing | -10 | 2026-11-06 | In progress | Threshold rule fixed after test 5. Retest booked.
7 | Tax | Check GST on the cart, checkout, emails and invoice | The total and the GST amount match in every place, for local and overseas orders. | All |  | Accounts | -10 | 2026-11-06 | Done
8 | Refunds | Refund a card order and a PayNow order in full | Money goes back, the refund email arrives, the accounting entry is right and GA4 receives a refund event. | All |  | Accounts | -8 | 2026-11-08 | Done | Stripe allows PayNow refunds up to 90 days after payment.
9 | Refunds | Make a partial refund | Only the refunded items or amount are returned, and stock is adjusted if items come back. | All |  | Accounts | -8 | 2026-11-08 | Not started
10 | Stock | Test out-of-stock and low-stock products | Out-of-stock products cannot be bought (or show a backorder date), and low-stock alerts reach the right person. | All |  | Ops lead | -8 | 2026-11-08 | In progress
11 | Checkout | Test guest checkout and account sign-up | Shoppers can buy without an account, and can create one after the order. | All |  | Agency | -8 | 2026-11-08 | Done
12 | Consent | Test the marketing consent box | Ticking it adds the customer to the email list with a record of consent. Leaving it unticked does not. | All |  | Marketing | -8 | 2026-11-08 | Done
13 | Emails | Check order emails land in the inbox | Emails arrive in Gmail and Outlook inboxes, not spam, and the sending domain has SPF, DKIM and DMARC records. | All |  | Agency | -10 | 2026-11-06 | Done
14 | Devices | Test the whole journey on phones | Browse, add to cart and pay on an iPhone and an Android phone. Phone and postal code fields open the number keyboard. | All |  | Ops lead | -8 | 2026-11-08 | In progress
Formulas:
Due date = IF(AND(ISNUMBER([Days from launch]),ISNUMBER('Start here'!$B15)),'Start here'!$B15+[Days from launch],"")

## Test orders
Test orders
One row per test order. Cover every payment method (including PayNow and an expired PayNow QR), every delivery option, a discount code, a trade order and a refund. Totals are for a fictional store.
# | Date | Scenario | Payment method | Delivery | Discount code | Expected total (S$) | Charged total (S$) | Totals match? | Emails received? | In GA4 once? | Refund tested? | Result | Notes
1 | 2026-11-06 | Retail order, 3 items, courier | Card (test) | Courier |  | 86.4 | 86.4 | Yes | Yes | Yes | No | Pass
2 | 2026-11-06 | Retail order, 1 item, self-collection | PayNow (test) | Self-collection | WELCOME10 | 21.6 | 21.6 | Yes | Yes | No | No | Fail | Purchase missing in GA4 after closing the tab. Purchase now sent from the server.
3 | 2026-11-07 | Retail order, PayNow QR left to expire | PayNow (test) | Courier |  | 54 |  |  | No | No | No | Pass | Not marked paid, stock released, no order email sent.
4 | 2026-11-07 | Trade order on 30-day terms | Invoice | Next-day (trade) |  | 412.5 | 412.5 | Yes | Yes | Yes | No | Pass
5 | 2026-11-08 | Retail order just above free delivery threshold | Card (test) | Courier |  | 81 | 89 | Check | Yes | Yes | Yes | Fail | Delivery charge added above the threshold. Rule fixed, retest booked.
6 | 2026-11-09 | Retest of test 2 after the server-side purchase fix | PayNow (test) | Self-collection | WELCOME10 | 21.6 | 21.6 | Yes | Yes | Yes | Yes | Pass

## Tracking
Tracking
GA4 ecommerce events and ad conversion tags. Each test order should be recorded once, with the right value.
# | Area | Task | Done when | Platform | Platform note | Owner | Days from launch | Due date | Status | Notes
1 | GA4 | Set up the GA4 property for the store | The store's data stream is live, your own visits are filtered out and the time zone and currency are Singapore and SGD. | All |  | Agency | -14 | 2026-11-02 | Done
2 | GA4 | Send the recommended ecommerce events | view_item_list, select_item, view_item, add_to_cart, view_cart, remove_from_cart, begin_checkout, add_shipping_info, add_payment_info, purchase and refund all appear in DebugView. | All | Shopify: customer events or an app. WooCommerce: a plugin or Google Tag Manager. Custom: push events from the code. | Agency | -10 | 2026-11-06 | Done
3 | GA4 | Use the order number as transaction_id | Each purchase sends its own order number, value, currency SGD, tax and shipping. Reloading the thank-you page does not count the order twice. | All |  | Agency | -10 | 2026-11-06 | Done | A fixed or empty transaction ID merges real orders together.
4 | GA4 | Check PayNow orders are counted | A PayNow test order appears in GA4 even if you close the browser tab after paying in the banking app. | All | If not, send the purchase from the server when the gateway confirms payment. | Agency | -8 | 2026-11-08 | Done | Purchase now sent from the server when the gateway confirms payment.
5 | GA4 | Mark purchase as a key event | In GA4 Admin, purchase is listed as a key event. | All |  | Agency | -8 | 2026-11-08 | Done
6 | Ads | Set up Google Ads and Meta purchase tags | Each test order is recorded once in each ad platform, with the order number as the ID and the same value as GA4. | All |  | Marketing | -7 | 2026-11-09 | In progress
7 | Links | Link GA4 with Google Ads and Search Console | Both links show as active in GA4 Admin. | All |  | Agency | -7 | 2026-11-09 | Done
8 | Consent | Match cookie and tracking settings to the privacy policy | Every tag on the site is named in the privacy policy, and the consent banner (if you use one) works on phones. | All |  | Director | -7 | 2026-11-09 | In progress
9 | Campaigns | Agree UTM naming before launch emails go out | Source, medium and campaign names are lower case and agreed. Campaign names avoid "shop" unless you want GA4's Shopping channel. | All |  | Marketing | -5 | 2026-11-11 | Not started | Free UTM builder: jin-design.com/resources/tools/utm-builder/
10 | Feeds | Submit a product feed for Google's free listings | Products are approved in Google Merchant Center with prices in SGD that match the site. | All |  | Marketing | -5 | 2026-11-11 | Not started | Optional.
Formulas:
Due date = IF(AND(ISNUMBER([Days from launch]),ISNUMBER('Start here'!$B15)),'Start here'!$B15+[Days from launch],"")

## Launch day
Launch day
The switch from test payments to live ones. Days from launch is 0 for every row.
# | Area | Task | Done when | Platform | Platform note | Owner | Days from launch | Due date | Status | Notes
1 | Backup | Take a backup or export before switching over | A full backup (WooCommerce, custom) or CSV exports and a theme copy (Shopify) are saved off the server. | All |  | Agency | 0 | 2026-11-16 | Not started
2 | Payments | Switch payments from test to live mode | Every payment method shows in live mode and test mode is off. | All |  | Agency | 0 | 2026-11-16 | Not started
3 | Orders | Cancel or archive test orders | Reports start clean, and test customers are removed or marked as tests. | All |  | Ops lead | 0 | 2026-11-16 | Not started
4 | Access | Open the store to customers and search engines | The storefront password or maintenance page is off, and nothing blocks search engines. | All | Shopify: remove the storefront password. WooCommerce: untick "Discourage search engines from indexing this site". Custom: remove noindex and staging blocks. | Agency | 0 | 2026-11-16 | Not started
5 | SEO | Switch on redirects from the old store | Every old product and category URL redirects to its new home in one step. | All |  | Agency | 0 | 2026-11-16 | Not started
6 | SEO | Submit the sitemap in Search Console | The sitemap lists only live product, category and content pages. | All |  | Agency | 0 | 2026-11-16 | Not started | Free sitemap checker: jin-design.com/resources/tools/sitemap-checker/
7 | Payments | Place real orders with a card and with PayNow, then refund them | Both orders are paid, emails arrive and both refunds go through. | All |  | Director | 0 | 2026-11-16 | Not started
8 | GA4 | Check GA4 Realtime | Each real order shows once as a purchase with the right value, and each refund shows as a refund. | All |  | Agency | 0 | 2026-11-16 | Not started
9 | Team | Name who answers customers today | Someone is watching order emails, WhatsApp and phone, with answers ready for delivery and payment questions. | All |  | Ops lead | 0 | 2026-11-16 | Not started
10 | Marketing | Announce the store to customers who opted in | Only customers who gave marketing consent receive the email, and it has an unsubscribe link. | All |  | Marketing | 0 | 2026-11-16 | Not started
Formulas:
Due date = IF(AND(ISNUMBER([Days from launch]),ISNUMBER('Start here'!$B15)),'Start here'!$B15+[Days from launch],"")

## First 30 days
First 30 days
Checks after launch. Days from launch counts forward from the launch date.
# | Area | Task | Done when | Platform | Platform note | Owner | Days from launch | Due date | Status | Notes
1 | Orders | Check every order is paid and dispatched | No order is stuck as unpaid or on hold, and PayNow orders are all marked paid. | All |  | Ops lead | 1 | 2026-11-17 | Not started | Daily for the first week.
2 | GA4 | Compare store orders with GA4 purchases | The number of orders and revenue in GA4 are close to the store admin for the same days. Investigate any gap. | All |  | Agency | 2 | 2026-11-18 | Not started | Repeat weekly for the first month.
3 | Customers | Turn customer questions into page updates | Questions asked by email or WhatsApp are answered on the product page, delivery page or FAQ. | All |  | Marketing | 3 | 2026-11-19 | Not started
4 | SEO | Check Search Console for errors | No spike in not found pages, redirect errors or blocked pages. | All |  | Agency | 7 | 2026-11-23 | Not started
5 | Accounts | Reconcile payouts with orders | Every payout from the gateway matches the orders and refunds in the accounting software. | All |  | Accounts | 10 | 2026-11-26 | Not started
6 | Checkout | Review where shoppers leave the checkout | The GA4 funnel from begin_checkout to purchase shows which step loses the most shoppers. Test that step on a phone. | All |  | Agency | 14 | 2026-11-30 | Not started
7 | Delivery | Review late or failed deliveries | Each late or failed delivery has a reason, and the courier or delivery promise is adjusted where needed. | All |  | Ops lead | 14 | 2026-11-30 | Not started
8 | Returns | Check returns and refunds followed the policy | Each request was handled within the policy, and the policy is updated if customers found it unclear. | All |  | Director | 14 | 2026-11-30 | Not started
9 | Upkeep | Review apps, plugins and scripts | Anything unused is removed, and every update has an owner and a schedule. | All | Shopify: apps and theme updates. WooCommerce: plugins, theme, WordPress and PHP. Custom: packages and server. | Agency | 21 | 2026-12-07 | Not started
10 | Speed | Check speed on phones | Core Web Vitals in Search Console: LCP 2.5 s or less, INP 200 ms or less, CLS 0.1 or less. Field data covers the previous 28 days. | All |  | Agency | 28 | 2026-12-14 | Not started
11 | Data | Delete test accounts and data you no longer need | Test customers and exports used during the build are deleted, in line with your retention policy. | All |  | Director | 30 | 2026-12-16 | Not started
12 | Review | Review the first month | Sales by product, channel and payment method are reviewed, and the next fixes are agreed and given owners. | All |  | Director | 30 | 2026-12-16 | Not started
Formulas:
Due date = IF(AND(ISNUMBER([Days from launch]),ISNUMBER('Start here'!$B15)),'Start here'!$B15+[Days from launch],"")